## Estimation Details
Phase | Tasks | Deliverables | Total | BA | Developer | Duration
Analysis & Design | Update to design document |  |  |  | 1 | 0
[6 empty] | 0 | 0
1
Development & Testing | User Interface
| 1. Provide the ability for the users to review the translation and correct the translations in Dashboard. 2. Save the corrected translation and record user actions to the database 3. Users will release the message with corrected translation to input queue for OFAC screening 4. Authentication using Active Directory |  |  |  | 10 | 10
WEI Service Changes
| Identify the messages that have CTC codes and move them to a review queue after the translation Query the database if the translation exists. If exists, the translation will be appended to message and the message sent to OFAC directly and not to review queue |  |  |  | 3 | 3
Database Changes
| 1. Create a table for storing the translations. 2. Script to insert/update the translations 3. Script to record user actions in the database |  |  |  | 1 | 1
14
14
Testing
| Functional and System Testing |  |  |  | 3
Documentation |  |  | 3
| Update the Installation Document |  |  |  | 1 | 0
| Update the User Manual |  |  |  | 1 | 0 | 0
| Build/Packaging and Deployment |  |  |  | 1
3
|  | Total | 21
Project Management |  |  | 0 | 0 |  |  | 0
Totals |  |  | 21 | 0 | 21 | 21
Assumptions